## Sheet1
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE |  | Bookworm deluxe |  |  |  |  | COMPANY NAME |  |  | UNIVERSITY OF CEBU , BANILAD CAMPUS
PROJECT MANAGER |  | Aaron Brent Abundo |  |  |  |  | DATE |  |  | 10/201/18
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 | [6 empty] | WEEK 2
[7 empty] | 2018-10-12 | 2018-10-13 | 2018-10-14 | 2018-10-15 | 2018-10-16 | 2018-10-17 | 2018-10-18 | 2018-10-19 | 2018-10-20 | 2018-10-21 | 2018-10-22 | 2018-10-23 | 2018-10-24
[7 empty] | FRI | SAT | SUN | MON | TUE | WED | THU | FRI | SAT | SUN | MON | TUE | WED
1 | PREPARING OF REQUIREMENTS
1.1 | Discussion | ALL MEMBERS INVOLVED | 2018-10-12 | 2018-10-12 | 1 | 100% | bar: 2018-10-12
1.2 | Research | ALL MEMBERS INVOLVED | 2018-10-12 | 2018-10-12 | 3 | 100% | bar: 2018-10-13
1.3 | Requirements | Jheia Codoy & Jane Arcilla | 2018-10-13 | 2018-10-13 | 3 | 100% | bar: 2018-10-13
1.4 | Gannt/WBS Chart | Jopet Louie Montero & Lucille Dominique Estocapio | 2018-10-13 | 2018-10-13 | 3 | 100% | bar: 2018-10-13
2 | PROJECT DESIGN
2.1 | UI Designing |  | 2018-10-14 | 2018-10-15 | 5
| Game Mechanics & About The Game UI | Jane Arcilla & Jheia Codoy | 2018-10-14 | 2018-10-15 | 5 | 100%
| Login & Main Menu UI | Hazel Jane Papas & Adrian Millor | 2018-10-14 | 2018-10-15 | 5 | 100%
| Statistics & Settings UI | Jopet Louie Montero & Lucille Dominique Estocapio | 2018-10-14 | 2018-10-15 | 5 | 100%
2.2 | Declaration of Boards in . Cs |  | 2018-10-14 | 2018-10-15 | 5
| Index Number 0 - 7 | Jane Arcilla & Jheia Codoy | 2018-10-14 | 2018-10-15 | 5 | 100%
| Index Number 8 - 15 | Hazel Jane Papas & Adrian Millor | 2018-10-14 | 2018-10-15 | 5 | 0%
| Index Number 16 - 23 | Jopet Louie Montero & Lucille Dominique Estocapio | 2018-10-14 | 2018-10-15 | 5 | 0%
2.3 | Dashboard Design | Aaron Brent Abundo | 2018-10-14 | 2018-10-15 | 5 | 100%
2.4 | Inventory Tab | Aaron Brent Abundo | 2018-10-14 | 2018-10-15 | 5 | 100%
2.5 | Confirm Tab | Aaron Brent Abundo | 2018-10-14 | 2018-10-15 | 5 | 100%
2.6 | Icons | Aaron Brent Abundo | 2018-10-14 | 2018-10-15 | 5 | 100%
3 | PROJECT IMPLEMENTATION
3.1 | Predefined Items | Hazel Jane Papas & Adrian Millor | 2018-10-17 | 2018-10-17 | 1 | 100% | bar: 2018-10-17
3.2 | Dashboard | Aaron Brent Abundo | 2018-10-18 | 2018-10-18 | 2 | 100% | bar: 2018-10-18
3.3 | Perform Inventory | Aaron Brent Abundo | 2018-10-19 | 2018-10-19 | 3 | 100% | bar: 2018-10-19
3.4 | View Inventory | Jheia Codoy & Jane Arcilla | 2018-10-20 | 2018-10-20 | 2 | 100% | bar: 2018-10-20
3.5 | Update Inventory | Jopet Louie Montero & Lucille Dominique Estocapio | 2018-10-21 | 2018-10-21 | 2 | 100% | bar: 2018-10-21
4 | PROJECT TESTING
4.1 | First Testing | Lucille Dominique Estocapio | 2018-10-22 | 2018-10-22 | 1 | 100% | bar: 2018-10-22
4.2 | First Debugging | Jane Arcilla | 2018-10-22 | 2018-10-22 | 1 | 100% | bar: 2018-10-22
4.3 | First Starting | Adrian Millor | 2018-10-22 | 2018-10-22 | 2 | 100% | bar: 2018-10-22
4.4 | Final Debugging | Hazel Jane Papas | 2018-10-23 | 2018-10-23 | 3 | 100% | bar: 2018-10-23
5 | PROJECT DEPLOYMENT
5.1 | Checking | ALL MEMBERS INVOLVED | 2018-10-24 | 2018-10-24 | 1 | 100% | bar: 2018-10-24